## Resumen
section | metric | displayValue | amount | hours | percentage | exactMinorUnits
Proyecto | Project number | EXAMPLE-P-001
Proyecto | Project name | EXAMPLE — Packaging Cell Commissioning
Proyecto | Client number | EXAMPLE-C-001
Proyecto | Client name | EXAMPLE — Example Manufacturing Ltd
Proyecto | Currency | USD
Proyecto | Period start | 2026-09-01
Proyecto | Period end | 2026-09-30
Proyecto | Billing model
Proyecto | Projection state
Economia del proyecto | Labor revenue
Economia del proyecto | Expense revenue
Economia del proyecto | Milestone revenue
Economia del proyecto | Revenue
Economia del proyecto | Internal labor cost
Economia del proyecto | Travel cost
Economia del proyecto | Other direct cost
Economia del proyecto | Direct cost | 985,00 US$ | 985 |  |  | 98500
Economia del proyecto | Worker compensation
Economia del proyecto | Contribution | 6.037,50 US$ | 6037.5 |  |  | 603750
Economia del proyecto | Contribution margin | 85.97% |  |  | 85.97
Economia del proyecto | Actual hours
Economia del proyecto | Approved hours
Economia del proyecto | Billable hours
Facturacion y cobro | Invoiced net
Facturacion y cobro | Invoiced gross
Facturacion y cobro | Collected | 4.210,00 US$ | 4210 |  |  | 421000
Facturacion y cobro | Receivable | 2.812,50 US$ | 2812.5 |  |  | 281250
Facturacion y cobro | Approved unbilled WIP
Facturacion y cobro | Unapproved WIP
Prevision | Budget
Prevision | Remaining cap
Prevision | Budget consumed
Prevision | Travel budget
Prevision | Estimate to complete
Prevision | Estimate at completion cost
Prevision | Estimate at completion revenue
Prevision | Expected final margin
Prevision | Forecast basis

## Mano de obra
worker | date | category | actualHours | actualMinutes | billableHours | billableMinutes | clientRevenue | internalCost | workerCompensation | billability | approval | billingStatus | invoiceId | clientRevenueExactMinor | internalCostExactMinor | workerCompensationExactMinor
|  | work | 8 | 480 | [7 empty] | invoiced | EXAMPLE-LABOR-001
|  | travel | 7.5 | 450 | [7 empty] | invoiced | EXAMPLE-LABOR-001

## Gastos
worker | date | category | paidBy | treatment | cost | actualCost | revenue | pendingFinanceRevenue | approval | financeApproval | projection | costExactMinor | actualCostExactMinor | revenueExactMinor | pendingFinanceRevenueExactMinor
|  | hotel | worker | reimbursable
|  | travel | worker | reimbursable

## WIP no facturado
sourceType | sourceId | date | workerId | amount | amountExactMinor

## Minimo diario
workerId | date | adjustmentHours | adjustmentMinutes | revenue | revenueExactMinor

## Facturas
invoiceNumber | stream | state | periodStart | periodEnd | currency | total | collected | issuedAt | dueAt | totalExactMinor | collectedExactMinor
EXAMPLE-LABOR-001 |  |  |  |  | USD | 1937.5 |  |  |  | 193750
EXAMPLE-EXPENSE-001 |  |  |  |  | USD | 210 |  |  |  | 21000
EXAMPLE-MILESTONE-001 |  |  |  |  | USD | 5000 |  |  |  | 500000
EXAMPLE-CREDIT-001 |  |  |  |  | USD | -125 |  |  |  | -12500

## Hitos
name | dueOn | state | amount | amountExactMinor
EXAMPLE commissioning milestone | 2026-09-30 | Aprobado | 5000 | 500000

## Alertas
code | sourceId