## Summary
Section | What this measures | Formatted value | Amount in project currency | Hours | Percent | Exact amount in minor units
Project | Project number | C-0050-P-20261005
Project | Project name | BBS · Ejemplo de manual
Project | Client number | C-0050
Project | Client name | BBS DEMO - Manual
Project | Currency | USD
Project | Period start | 2026-10-01
Project | Period end | 2026-10-05
Project | Billing model | tm
Project | Projection state | ready
Project economics | Potential labor charges to client | $4,490.00 | 4490 |  |  | 449000
Project economics | Finance-approved expense charges to client | $182.00 | 182 |  |  | 18200
Project economics | Approved milestone charges to client | $0.00 | 0 |  |  | 0
Project economics | Potential total charges to client | $4,672.00 | 4672 |  |  | 467200
Project economics | Internal labor cost | $1,520.00 | 1520 |  |  | 152000
Project economics | Travel cost | $180.00 | 180 |  |  | 18000
Project economics | Other direct cost | $50.00 | 50 |  |  | 5000
Project economics | Approved direct company cost | $1,750.00 | 1750 |  |  | 175000
Project economics | Worker compensation | $2,100.00 | 2100 |  |  | 210000
Project economics | Contribution | $2,922.00 | 2922 |  |  | 292200
Project economics | Contribution margin | 62.54% |  |  | 62.54
Project economics | Actual hours | 42.50 |  | 42.5
Project economics | Approved hours | 42.50 |  | 42.5
Project economics | Billable hours | 42.50 |  | 42.5
Billing and collections | Invoiced to client before tax | $0.00 | 0 |  |  | 0
Billing and collections | Invoiced to client including tax | $0.00 | 0 |  |  | 0
Billing and collections | Payments collected from client | $0.00 | 0 |  |  | 0
Billing and collections | Outstanding client balance | $0.00 | 0 |  |  | 0
Billing and collections | Approved charges not yet invoiced | $4,672.00 | 4672 |  |  | 467200
Billing and collections | Potential charges awaiting approval | $0.00 | 0 |  |  | 0
Forecast | Budget
Forecast | Remaining cap
Forecast | Budget consumed
Forecast | Travel budget
Forecast | Expense budget
Forecast | Expense budget consumed
Forecast | Estimate to complete
Forecast | Estimate at completion cost
Forecast | Estimate at completion revenue
Forecast | Expected final margin
Forecast | Forecast basis | No detailed plan configured
How to read this file | Amount entered from receipt | The source expense amount, even when approval, reimbursement or client billing is not configured.
How to read this file | Calculated worker reimbursement | Blank until a reimbursement amount is configured; it is not proof of payment.
How to read this file | Amount actually reimbursed | Shown only when the reimbursement is marked reimbursed.
How to read this file | Potential client charge | An estimate from the rate or billing rule; check Invoices and Invoice expenses for amounts actually placed on an invoice.
How to read this file | Zero versus blank | Zero is a calculated value. Blank means the amount is not configured or not yet available.

## Labor
Worker | Work date | Time category | Hours recorded | Minutes recorded | Hours eligible to charge client | Minutes eligible to charge client | Potential amount to charge client | Calculated internal labor cost | Calculated worker compensation | Client billing eligibility | Time approval status | Billing status | Linked invoice ID | Potential client charge (minor units) | Internal labor cost (minor units) | Worker compensation (minor units)
BBS DEMO - Jefe de crew | 2026-10-02 | commissioning | 8 | 480 | 8 | 480 | 640 | 360 | 320 | billable | Approved | unlocked |  | 64000 | 36000 | 32000
BBS DEMO - Tecnico 1 | 2026-10-02 | regular | 8 | 480 | 8 | 480 | 480 | 280 | 240 | billable | Approved | unlocked |  | 48000 | 28000 | 24000
BBS DEMO - Tecnico 2 | 2026-10-02 | regular | 8 | 480 | 8 | 480 | 440 | 240 | 900 | billable | Approved | unlocked |  | 44000 | 24000 | 90000
BBS DEMO - Jefe de crew | 2026-10-03 | overtime | 2 | 120 | 2 | 120 | 160 | 90 | 80 | billable | Approved | unlocked |  | 16000 | 9000 | 8000
BBS DEMO - Tecnico 1 | 2026-10-03 | travel | 3 | 180 | 3 | 180 | 180 | 105 | 240 | billable | Approved | unlocked |  | 18000 | 10500 | 24000
BBS DEMO - Tecnico 2 | 2026-10-03 | travel | 6 | 360 | 6 | 360 | 330 | 180 | 0 | billable | Approved | unlocked |  | 33000 | 18000 | 0
BBS DEMO - Jefe de crew | 2026-10-05 | regular | 1.5 | 90 | 1.5 | 90 | 120 | 67.5 | 60 | billable | Approved | unlocked |  | 12000 | 6750 | 6000
BBS DEMO - Jefe de crew | 2026-10-05 | regular | 0.5 | 30 | 0.5 | 30 | 40 | 22.5 | 20 | billable | Approved | unlocked |  | 4000 | 2250 | 2000
BBS DEMO - Tecnico 1 | 2026-10-05 | regular | 1.5 | 90 | 1.5 | 90 | 600 | 52.5 | 240 | billable | Approved | unlocked |  | 60000 | 5250 | 24000
BBS DEMO - Tecnico 1 | 2026-10-05 | regular | 0.5 | 30 | 0.5 | 30 | 0 | 17.5 | 0 | billable | Approved | unlocked |  | 0 | 1750 | 0
BBS DEMO - Tecnico 2 | 2026-10-05 | regular | 2 | 120 | 2 | 120 | 1500 | 60 | 0 | billable | Approved | unlocked |  | 150000 | 6000 | 0
BBS DEMO - Tecnico 2 | 2026-10-05 | regular | 1.5 | 90 | 1.5 | 90 | 0 | 45 | 0 | billable | Approved | unlocked |  | 0 | 4500 | 0

## Expenses
Expense record ID | Worker | Expense date | Expense category | Expense description | Who paid at purchase | Currency of receipt | Amount entered from receipt | Calculated worker reimbursement | Amount actually reimbursed | Reimbursement status | Client charge treatment | Finance classification status | Approved company cost | Calculated company cost | Finance-approved client charge | Client charge awaiting finance approval | Expense approval status | Finance approval status | Finance calculation status | Linked invoice ID | Receipt amount (minor units) | Calculated reimbursement (minor units) | Paid reimbursement (minor units) | Approved company cost (minor units) | Calculated company cost (minor units) | Finance-approved client charge (minor units) | Pending client charge (minor units)
01a10c58-33ad-757d-ae1f-d5a848572979 | BBS DEMO - Tecnico 1 | 2026-10-02 | hotel | DEMO MANUAL - Alojamiento, reembolso y cobro al coste | worker | USD | 100 | 100 |  | pending | reimbursable_at_cost | classified | 100 | 100 | 100 | 0 | Approved | approved | ready |  | 10000 | 10000 |  | 10000 | 10000 | 10000 | 0
01a10c58-3a65-72ac-8f85-a78f49be9194 | BBS DEMO - Tecnico 1 | 2026-10-02 | meals | DEMO MANUAL - Recibo compartido de crew, 30 USD por cada tecnico | worker | USD | 60 | 60 |  | pending | reimbursable_at_cost | classified | 60 | 60 | 60 | 0 | Approved | approved | ready |  | 6000 | 6000 |  | 6000 | 6000 | 6000 | 0
01a10c58-325a-76df-9a7d-7dc23eab2129 | BBS DEMO - Jefe de crew | 2026-10-02 | parking | DEMO MANUAL - Aparcamiento, reembolso y cobro al cliente con 10% de margen | worker | USD | 20 | 20 |  | pending | reimbursable_plus_markup | classified | 20 | 20 | 22 | 0 | Approved | approved | ready |  | 2000 | 2000 |  | 2000 | 2000 | 2200 | 0
01a10c58-3957-779a-91d7-1d67c62ef823 | BBS DEMO - Tecnico 2 | 2026-10-03 | tools | DEMO MANUAL - Herramientas pagadas por empresa, incluidas y sin reembolso | company_card | USD | 50 | 0 |  | not_applicable | all_in | classified | 50 | 50 | 0 | 0 | Approved | approved | ready |  | 5000 | 0 |  | 5000 | 5000 | 0 | 0

## Unbilled WIP
Record type | Record ID | Work or expense date | Worker ID | Approved amount not yet invoiced | Unbilled amount (minor units)
time | 01a10c58-30da-7535-93cd-f195682111d6 | 2026-10-02 | 01a10c51-9ff2-77d1-a994-de141701efe3 | 640 | 64000
time | 01a10c58-2f82-74a8-b7e8-2eed009c0bd2 | 2026-10-02 | 01a10c51-a140-707b-9210-21b341b4d4ee | 480 | 48000
time | 01a10c58-2f87-7738-b3ee-f182a6dcd5fc | 2026-10-02 | 01a10c51-a2ad-74c8-ae12-e377be6b6942 | 440 | 44000
time | 01a10c58-319c-75be-be39-c80a86b3ac9c | 2026-10-03 | 01a10c51-9ff2-77d1-a994-de141701efe3 | 160 | 16000
time | 01a10c58-2fc6-73fe-b2b0-31d42c13f841 | 2026-10-03 | 01a10c51-a140-707b-9210-21b341b4d4ee | 180 | 18000
time | 01a10c58-2fc9-71d8-8217-97e14b326405 | 2026-10-03 | 01a10c51-a2ad-74c8-ae12-e377be6b6942 | 330 | 33000
time | 01a10cb5-e33e-718e-8807-30d8cab2fda2 | 2026-10-05 | 01a10c51-9ff2-77d1-a994-de141701efe3 | 120 | 12000
time | 01a10cb5-e54d-7051-a32d-6ea8d30a6d9e | 2026-10-05 | 01a10c51-9ff2-77d1-a994-de141701efe3 | 40 | 4000
time | 01a10cb5-e6e8-7685-9945-809331ce5f53 | 2026-10-05 | 01a10c51-a140-707b-9210-21b341b4d4ee | 600 | 60000
time | 01a10cb5-e815-774c-8669-ce3ee7ef9d86 | 2026-10-05 | 01a10c51-a140-707b-9210-21b341b4d4ee | 0 | 0
time | 01a10cb5-e933-73cb-9c8a-6580bd8c7fbc | 2026-10-05 | 01a10c51-a2ad-74c8-ae12-e377be6b6942 | 1500 | 150000
time | 01a10cb5-eac6-75c5-8520-3fc90b608229 | 2026-10-05 | 01a10c51-a2ad-74c8-ae12-e377be6b6942 | 0 | 0
expense | 01a10c58-33ad-757d-ae1f-d5a848572979 | 2026-10-02 | 01a10c51-a140-707b-9210-21b341b4d4ee | 100 | 10000
expense | 01a10c58-3a65-72ac-8f85-a78f49be9194 | 2026-10-02 | 01a10c51-a140-707b-9210-21b341b4d4ee | 60 | 6000
expense | 01a10c58-325a-76df-9a7d-7dc23eab2129 | 2026-10-02 | 01a10c51-9ff2-77d1-a994-de141701efe3 | 22 | 2200

## Daily minimum
Worker ID | Work date | Extra billable hours from daily minimum | Extra billable minutes from daily minimum | Potential client charge from daily minimum | Daily minimum charge (minor units)

## Invoices
Invoice number | Billing stream | Invoice status | Service period start | Service period end | Invoice currency | Invoice total including tax | Expense lines on invoice | Expense lines charged to client | Payments collected | Issued date | Due date | Invoice total (minor units) | Invoiced expense lines (minor units) | Collected payments (minor units)
| labor | Draft | 2026-10-05 | 2026-10-11 | USD | 2260 | 0 | 0 | 0 |  |  | 226000 | 0 | 0
| labor | Draft | 2026-10-01 | 2026-10-04 | USD | 2230 | 0 | 0 | 0 |  |  | 223000 | 0 | 0
| expense | Draft | 2026-10-01 | 2026-10-31 | USD | 182 | 3 | 182 | 0 |  |  | 18200 | 18200 | 0

## Invoice expenses
Invoice number | Invoice ID | Invoice status | Source expense ID | Line charged to client | Invoice currency | Expense amount on invoice | Invoiced expense (minor units)
| 01a10c5d-83ff-72a2-988d-7ad68220b383 | Draft | 01a10c58-325a-76df-9a7d-7dc23eab2129 | 2026-10-02 · Parking ficticio DEMO · parking | USD | 22 | 2200
| 01a10c5d-83ff-72a2-988d-7ad68220b383 | Draft | 01a10c58-33ad-757d-ae1f-d5a848572979 | 2026-10-02 · Hotel ficticio DEMO · hotel | USD | 100 | 10000
| 01a10c5d-83ff-72a2-988d-7ad68220b383 | Draft | 01a10c58-3a65-72ac-8f85-a78f49be9194 | 2026-10-02 · Restaurante ficticio DEMO · meals | USD | 60 | 6000

## Milestones
Milestone | Due date | Approval status | Milestone amount to charge client | Milestone amount (minor units)

## Alerts
Finance alert code | Affected record ID