## Resumo
section | metric | displayValue | amount | hours | percentage | exactMinorUnits
Projeto | Project number | SYN-C-0001-P-001
Projeto | Project name | Synthetic commissioning validation
Projeto | Client number
Projeto | Client name | Synthetic Client One
Projeto | Currency | USD
Projeto | Period start | 2026-08-01
Projeto | Period end | 2026-08-31
Projeto | Billing model
Projeto | Projection state
Economia do projeto | Labor revenue | US$ 800,00 | 800 |  |  | 80000
Economia do projeto | Expense revenue
Economia do projeto | Milestone revenue
Economia do projeto | Revenue
Economia do projeto | Internal labor cost
Economia do projeto | Travel cost
Economia do projeto | Other direct cost
Economia do projeto | Direct cost | US$ 485,00 | 485 |  |  | 48500
Economia do projeto | Worker compensation
Economia do projeto | Contribution | US$ 315,00 | 315 |  |  | 31500
Economia do projeto | Contribution margin | 39.38% |  |  | 39.38
Economia do projeto | Actual hours | 8.00 |  | 8
Economia do projeto | Approved hours | 8.00 |  | 8
Economia do projeto | Billable hours | 8.00 |  | 8
Faturamento e cobranca | Invoiced net
Faturamento e cobranca | Invoiced gross
Faturamento e cobranca | Collected
Faturamento e cobranca | Receivable
Faturamento e cobranca | Approved unbilled WIP
Faturamento e cobranca | Unapproved WIP
Previsao | Budget
Previsao | Remaining cap
Previsao | Budget consumed
Previsao | Travel budget
Previsao | Estimate to complete
Previsao | Estimate at completion cost
Previsao | Estimate at completion revenue
Previsao | Expected final margin
Previsao | Forecast basis

## Mao de obra
worker | date | category | actualHours | actualMinutes | billableHours | billableMinutes | clientRevenue | internalCost | workerCompensation | billability | approval | billingStatus | invoiceId | clientRevenueExactMinor | internalCostExactMinor | workerCompensationExactMinor
Synthetic Worker 1 | 2026-08-12 | regular | 8 | 480 | 8 | 480 | 800 | 400 | 320 |  | Aprovado |  |  | 80000 | 40000 | 32000

## Despesas
worker | date | category | paidBy | treatment | cost | actualCost | revenue | pendingFinanceRevenue | approval | financeApproval | projection | costExactMinor | actualCostExactMinor | revenueExactMinor | pendingFinanceRevenueExactMinor
Synthetic Worker 1 | 2026-08-12 | travel | worker | reimbursable | 85 |  | 85 |  | Aprovado | approved | ready | 8500 |  | 8500

## WIP nao faturado
sourceType | sourceId | date | workerId | amount | amountExactMinor

## Minimo diario
workerId | date | adjustmentHours | adjustmentMinutes | revenue | revenueExactMinor

## Faturas
invoiceNumber | stream | state | periodStart | periodEnd | currency | total | collected | issuedAt | dueAt | totalExactMinor | collectedExactMinor
SYN-LAB-0001 | labor |  |  |  | USD

## Marcos
name | dueOn | state | amount | amountExactMinor

## Alertas
code | sourceId