## Summary
section | metric | displayValue | amount | hours | percentage | exactMinorUnits
Project | Project number | EXAMPLE-P-001
Project | Project name | EXAMPLE — Packaging Cell Commissioning
Project | Client number | EXAMPLE-C-001
Project | Client name | EXAMPLE — Example Manufacturing Ltd
Project | Currency | USD
Project | Period start | 2026-09-01
Project | Period end | 2026-09-30
Project | Billing model
Project | Projection state
Project economics | Labor revenue
Project economics | Expense revenue
Project economics | Milestone revenue
Project economics | Revenue
Project economics | Internal labor cost
Project economics | Travel cost
Project economics | Other direct cost
Project economics | Direct cost | $985.00 | 985 |  |  | 98500
Project economics | Worker compensation
Project economics | Contribution | $6,037.50 | 6037.5 |  |  | 603750
Project economics | Contribution margin | 85.97% |  |  | 85.97
Project economics | Actual hours
Project economics | Approved hours
Project economics | Billable hours
Billing and collections | Invoiced net
Billing and collections | Invoiced gross
Billing and collections | Collected | $4,210.00 | 4210 |  |  | 421000
Billing and collections | Receivable | $2,812.50 | 2812.5 |  |  | 281250
Billing and collections | Approved unbilled WIP
Billing and collections | Unapproved WIP
Forecast | Budget
Forecast | Remaining cap
Forecast | Budget consumed
Forecast | Travel budget
Forecast | Estimate to complete
Forecast | Estimate at completion cost
Forecast | Estimate at completion revenue
Forecast | Expected final margin
Forecast | Forecast basis

## Labor
worker | date | category | actualHours | actualMinutes | billableHours | billableMinutes | clientRevenue | internalCost | workerCompensation | billability | approval | billingStatus | invoiceId | clientRevenueExactMinor | internalCostExactMinor | workerCompensationExactMinor
|  | work | 8 | 480 | [7 empty] | invoiced | EXAMPLE-LABOR-001
|  | travel | 7.5 | 450 | [7 empty] | invoiced | EXAMPLE-LABOR-001

## Expenses
worker | date | category | paidBy | treatment | cost | actualCost | revenue | pendingFinanceRevenue | approval | financeApproval | projection | costExactMinor | actualCostExactMinor | revenueExactMinor | pendingFinanceRevenueExactMinor
|  | hotel | worker | reimbursable
|  | travel | worker | reimbursable

## Unbilled WIP
sourceType | sourceId | date | workerId | amount | amountExactMinor

## Daily minimum
workerId | date | adjustmentHours | adjustmentMinutes | revenue | revenueExactMinor

## Invoices
invoiceNumber | stream | state | periodStart | periodEnd | currency | total | collected | issuedAt | dueAt | totalExactMinor | collectedExactMinor
EXAMPLE-LABOR-001 |  |  |  |  | USD | 1937.5 |  |  |  | 193750
EXAMPLE-EXPENSE-001 |  |  |  |  | USD | 210 |  |  |  | 21000
EXAMPLE-MILESTONE-001 |  |  |  |  | USD | 5000 |  |  |  | 500000
EXAMPLE-CREDIT-001 |  |  |  |  | USD | -125 |  |  |  | -12500

## Milestones
name | dueOn | state | amount | amountExactMinor
EXAMPLE commissioning milestone | 2026-09-30 | Approved | 5000 | 500000

## Alerts
code | sourceId